# Consulting OS Core 3: Playbooks, Model, Recommend, Deck, Rhythm and Close

Each playbook is one task. In Gemini, trigger one by saying: Run the [name] playbook. Follow its questions, process and template. Deliver in chat.

# Section A: Model, recommend, storyline and deck

## Playbook: Initiative Sizing (name: initiative-sizing)

### Quick Start

Say: Run the initiative-sizing playbook Then provide: 1. The initiatives (or point me to the driver tree) 2. Baseline and benchmark data 3. Evidence for uplift (pilots, peers, interviews)

I will size each initiative on a common basis (run-rate EBITDA, one-time cost, ramp, confidence), show Low/Base/High, and rank by value and ease.

Output: Delivered in chat. Export to Google Docs or Sheets and file in the client Outputs folder. Time: ~35 min

When to use: Develop phase, before the Solutions SteerCo

Phase: Develop

### Step 1: Diagnostic Questions

Instead of a generic intake, I ask only what the files cannot answer:

#### Question 1: The Evidence

"What evidence supports the uplift: pilot, peer, expert, or assumption?"

Weight confidence by evidence type.

#### Question 2: The Cash

"What one-time cost and which year does it hit?"

Value without cost is not a business case.

### The Process

#### Step 1: Define each initiative

Scope, owner, mechanism, baseline.

#### Step 2: Size run-rate value

Baseline x uplift x flow-through; Low / Base / High.

#### Step 3: Add ramp and cost

Year-by-year ramp; one-time cost phasing.

#### Step 4: Apply a haircut

Confidence-weight; mark overlaps to avoid double counting.

#### Step 5: Rank

Value vs ease; sum with overlap removed.

### Common Mistakes

- Double counting: Two initiatives that move the same cost line must be netted.

- Gross vs net: Show EBITDA after flow-through, not revenue.

### Structured Output Template

# Initiative Sizing: [Engagement]

## So-What
[Total run-rate EBITDA range and one-time cost]

| Initiative | Mechanism | Baseline | Uplift (L/B/H) | Flow-through | Run-rate EBITDA (L/B/H) | One-time cost | Ramp | Confidence | Evidence |
|---|---|---|---|---|---|---|---|---|---|

## Overlaps Removed
[ ]

## Ranking
| Initiative | Value | Ease | Priority |
|---|---|---|---|

### Output Integration

#### Cross-Skill Integration

Feeds into: - the model-spec playbook - Model inputs - the options-evaluation playbook - Options to rank - the roadmap-build playbook - Sequence

Pulls from: - the value-driver-tree playbook - Levers - the benchmark-analysis playbook - Gap - the fact-base playbook - Baseline

When this output goes to a teammate or reviewer, attach a handoff cover note: Brief, Backup, So-what, Ask. Never send a page without all four.

### Output Quality Self-Check

Before delivering, verify:

- ☐ Run-rate and one-time are separated

- ☐ Low/Base/High shown

- ☐ Overlaps removed

- ☐ Evidence type is stated

- ☐ Baseline ties to the fact base

- ☐ Answer first: the so-what leads, the detail follows

- ☐ Sourced: every number and claim has a source or is marked as an assumption

- ☐ Voice: no em dashes; none of delve, leverage, utilize, unlock, harness, streamline, robust, cutting-edge

### Related Skills

- model-spec - Plan the model

- options-evaluation - Rank

- scenario-sensitivity - Stress test

## Playbook: Model Spec (name: model-spec)

### Quick Start

Say: Run the model-spec playbook Then provide: 1. The three questions the model must answer 2. Inputs and sources 3. Audience and decisions

I will write a one-to-two page spec that a second person could build from, including tabs, input list, logic, outputs, checks, and the review plan.

Output: Delivered in chat. Export to Google Docs or Sheets and file in the client Outputs folder. Time: ~25 min

When to use: Before any model is built, and when scope of a model changes

Phase: Mobilize through Develop

### Step 1: Diagnostic Questions

Instead of a generic intake, I ask only what the files cannot answer:

#### Question 1: The Questions

"What three questions must this model answer?"

A model with no stated question becomes a data dump.

#### Question 2: The Granularity

"Monthly, quarterly, or annual? By segment or total?"

Granularity drives size and error risk.

### The Process

#### Step 1: State the questions and audience

Who will use the outputs and for what decision.

#### Step 2: Sketch the structure

Tabs and flow: Cover, Guide, Inputs, Calc, Scenarios, Outputs, Checks, Log.

#### Step 3: List inputs

Each with unit, source, owner, scenario values.

#### Step 4: Describe calculations

In words and in formula pattern per block.

#### Step 5: Define outputs and checks

Outputs by slide; integrity and sense checks; owner; reviewer.

### Structured Output Template

# Model Spec: [Model]

**Owner:** [ ]  |  **Reviewer:** [ ]  |  **Version:** [ ]

## Questions
1. [ ]

## Structure
| Tab | Purpose | Inputs from | Outputs to |
|---|---|---|---|

## Inputs
| Ref | Input | Unit | Low | Base | High | Source | Owner |
|---|---|---|---|---|---|---|---|

## Calculation Logic
[Blocks and formulas in words]

## Outputs
| Output | Used on slide | Definition |
|---|---|---|

## Checks
| Check | Test | Tolerance |
|---|---|---|

## Review Plan
[Independent review method and date]

### Output Integration

#### Cross-Skill Integration

Feeds into: - the model-build playbook - Spec to build - the model-audit playbook - Audit reference - the scenario-sensitivity playbook - Scenario design

Pulls from: - the fact-base playbook - Baselines - the initiative-sizing playbook - Logic

When this output goes to a teammate or reviewer, attach a handoff cover note: Brief, Backup, So-what, Ask. Never send a page without all four.

### Output Quality Self-Check

Before delivering, verify:

- ☐ Three questions are stated

- ☐ Inputs have unit and source

- ☐ Checks are defined before building

- ☐ Owner and reviewer named

- ☐ Starter template is used: the model starter template (inputs, calc, scenarios, outputs, checks, log tabs)

- ☐ Answer first: the so-what leads, the detail follows

- ☐ Sourced: every number and claim has a source or is marked as an assumption

- ☐ Voice: no em dashes; none of delve, leverage, utilize, unlock, harness, streamline, robust, cutting-edge

### Related Skills

- model-build - Build it

- model-audit - Audit it

- scenario-sensitivity - Stress it

## Playbook: Model Build (name: model-build)

### Quick Start

Say: Run the model-build playbook Then provide: 1. The model spec 2. Input data (clean and sourced) 3. The starter file (default: the model starter template (inputs, calc, scenarios, outputs, checks, log tabs))

I will build the workbook with openpyxl from the spec, recalculate with LibreOffice, confirm zero errors and green checks, and hand it over with a guide tab.

Output: Delivered in chat. Export to Google Docs or Sheets and file in the client Outputs folder. Time: ~45 to 90 min depending on size

When to use: After the spec is agreed

Phase: Develop

### Step 1: Diagnostic Questions

Instead of a generic intake, I ask only what the files cannot answer:

#### Question 1: The Reviewer

"Who reviews the model independently, and when?"

Review is planned, not optional.

### The Process

#### Step 1: Copy the starter

Never build from a blank sheet; keep Cover, Guide, Inputs, Calc, Scenarios, Outputs, Checks, Log.

#### Step 2: Enter inputs

Blue font, one cell per assumption, unit, source, owner, date, confidence.

#### Step 3: Build calculations

One formula per row copied across; no hardcodes; no merged cells; no OFFSET or INDIRECT.

#### Step 4: Build outputs and checks

Outputs tab feeds slides; checks roll up to a master flag on the Cover.

#### Step 5: Recalculate and test

Run LibreOffice recalc; confirm zero errors; flex inputs and watch outputs move sensibly.

### Common Mistakes

- Typing numbers into formulas: Every number lives on the Inputs tab.

- Silent circularity: No circular references; use explicit iteration blocks if needed and document them.

### Structured Output Template

# Model Build Note: [Model]

**File:** [name]  |  **Owner:** [ ]  |  **Version:** [ ]

## What was built
[Tabs and logic]

## Recalc Result
Errors: [0]  |  Integrity flags: [0]  |  Sense flags: [ ]

## Tests Run
| Test | Input change | Expected | Observed |
|---|---|---|---|

## Known Limits
[ ]

## Next Step
[Independent audit by [name]]

### Output Integration

#### Cross-Skill Integration

Feeds into: - the model-audit playbook - File to audit - the number-tie-out playbook - Outputs to tie - the scenario-sensitivity playbook - Live model

Pulls from: - the model-spec playbook - Spec - the data-exploration playbook - Clean data

When this output goes to a teammate or reviewer, attach a handoff cover note: Brief, Backup, So-what, Ask. Never send a page without all four.

### Output Quality Self-Check

Before delivering, verify:

- ☐ Zero errors after recalculation

- ☐ No hardcodes in formulas

- ☐ Inputs sourced and dated

- ☐ Checks tab rolls up to the Cover

- ☐ Guide tab explains the model

- ☐ File name follows [Model]_[STATUS]_[vDATE]_[initials].xlsx

- ☐ Answer first: the so-what leads, the detail follows

- ☐ Sourced: every number and claim has a source or is marked as an assumption

- ☐ Voice: no em dashes; none of delve, leverage, utilize, unlock, harness, streamline, robust, cutting-edge

### Related Skills

- model-audit - Audit the model

- number-tie-out - Tie numbers

- scenario-sensitivity - Run scenarios

## Playbook: Model Audit (name: model-audit)

### Quick Start

Say: Run the model-audit playbook Then provide: 1. The model file 2. The spec and sources 3. Reasonableness anchors (benchmarks, reported totals)

I will test the model five ways and return a findings list with severity, location, and fix, plus a sign-off recommendation.

Output: Delivered in chat. Export to Google Docs or Sheets and file in the client Outputs folder. Time: ~40 min

When to use: Before any model output goes to the client

Phase: Develop and Recommend

### Step 1: Diagnostic Questions

Instead of a generic intake, I ask only what the files cannot answer:

#### Question 1: The Anchor

"What reported figure or benchmark should the base case be near?"

A model that lands far from anchors needs explaining.

### The Process

#### Step 1: Inputs vs sources

Sample every input back to its source.

#### Step 2: Formula review

Pattern consistency across rows, hardcodes, ranges, units, signs.

#### Step 3: Output vs benchmark

Compare to reported results and peer ranges.

#### Step 4: Back-of-envelope

Rebuild the answer in 10 lines; compare.

#### Step 5: Standards check

Colors, structure, checks, log; then sign-off recommendation.

### Structured Output Template

# Model Audit: [Model]

**Auditor:** [ ]  |  **Date:** [ ]  |  **Version audited:** [ ]

## Verdict
[Ready / Ready after fixes / Not ready]

## Findings
| # | Severity (H/M/L) | Tab / cell | Issue | Impact | Fix | Status |
|---|---|---|---|---|---|---|

## Tests Run
| Method | Result |
|---|---|
| Inputs vs sources | |
| Formulas | |
| Outputs vs benchmark | |
| Back-of-envelope | |
| Standards | |

### Output Integration

#### Cross-Skill Integration

Feeds into: - the model-build playbook - Fixes - the number-tie-out playbook - Cleared outputs

Pulls from: - the model-spec playbook - Intent - the fact-base playbook - Anchors

When this output goes to a teammate or reviewer, attach a handoff cover note: Brief, Backup, So-what, Ask. Never send a page without all four.

### Output Quality Self-Check

Before delivering, verify:

- ☐ Five methods were run

- ☐ Each finding has location and fix

- ☐ Severity reasoning is stated

- ☐ Sign-off recommendation is explicit

- ☐ Answer first: the so-what leads, the detail follows

- ☐ Sourced: every number and claim has a source or is marked as an assumption

- ☐ Voice: no em dashes; none of delve, leverage, utilize, unlock, harness, streamline, robust, cutting-edge

### Related Skills

- model-build - Apply fixes

- number-tie-out - Re-tie numbers

- scenario-sensitivity - Stress after fixes

## Playbook: Scenario and Sensitivity Analysis (name: scenario-sensitivity)

### Quick Start

Say: Run the scenario-sensitivity playbook Then provide: 1. The model and its key outputs 2. The uncertain assumptions 3. The decision threshold (what NPV or margin changes the decision)

I will run Low/Base/High scenarios and one-at-a-time sensitivities, produce a tornado ranking, and identify the break-even conditions.

Output: Delivered in chat. Export to Google Docs or Sheets and file in the client Outputs folder. Time: ~25 min

When to use: Before a financial case goes to the SteerCo

Phase: Develop and Recommend

### Step 1: Diagnostic Questions

Instead of a generic intake, I ask only what the files cannot answer:

#### Question 1: The Threshold

"At what value does the decision flip?"

Break-even is more useful than a fan of cases.

### The Process

#### Step 1: Define scenarios

Low, Base, High with a narrative each, not just numbers.

#### Step 2: Run the cases

Switch the selector; paste outputs as values into the Log tab with date.

#### Step 3: Run one-at-a-time sensitivities

Vary each key input by a fixed range; record effect on the output.

#### Step 4: Rank

Tornado of effects; top three assumptions named.

#### Step 5: Find break-evens

Input value at which the decision flips.

### Structured Output Template

# Scenario and Sensitivity: [Model]

## So-What
[Answer holds in Low case / flips if X falls below Y]

## Scenarios
| Scenario | Narrative | Key inputs | Output (NPV / EBITDA) |
|---|---|---|---|

## Sensitivity (tornado)
| Input | Low | High | Output at low | Output at high | Swing |
|---|---|---|---|---|---|

## Break-evens
[ ]

### Output Integration

#### Cross-Skill Integration

Feeds into: - the slide-draft playbook - Charts - the recommendation playbook - Risk-adjusted case - the risk-register playbook - Key assumptions

Pulls from: - the model-build playbook - Model - the initiative-sizing playbook - Ranges

When this output goes to a teammate or reviewer, attach a handoff cover note: Brief, Backup, So-what, Ask. Never send a page without all four.

### Output Quality Self-Check

Before delivering, verify:

- ☐ Scenario narratives exist

- ☐ Ranges have a source

- ☐ Break-even is stated

- ☐ Results are pasted as values with date

- ☐ Answer first: the so-what leads, the detail follows

- ☐ Sourced: every number and claim has a source or is marked as an assumption

- ☐ Voice: no em dashes; none of delve, leverage, utilize, unlock, harness, streamline, robust, cutting-edge

### Related Skills

- recommendation - Use in the recommendation

- slide-draft - Visualize

- risk-register - Log key risks

## Playbook: Number Tie-Out (name: number-tie-out)

### Quick Start

Say: Run the number-tie-out playbook Then provide: 1. The deck (pptx or text) 2. The model and fact base 3. Version

I will extract each number on each slide, trace it to a model cell or source, flag mismatches and rounding issues, and give you a signed tie-out log.

Output: Delivered in chat. Export to Google Docs or Sheets and file in the client Outputs folder. Time: ~30 min for a 20-page deck

When to use: Before every SteerCo and the final readout; after any model change

Phase: Develop through Transition

### Step 1: Diagnostic Questions

Instead of a generic intake, I ask only what the files cannot answer:

#### Question 1: The Rounding Rule

"One decimal for $M, whole % for shares, or something else?"

Consistency prevents fake mismatches.

### The Process

#### Step 1: Extract numbers

Per slide: value, unit, label, chart or text.

#### Step 2: Trace each

To model cell or document and page.

#### Step 3: Compare

Value, unit, rounding, period, definition.

#### Step 4: Flag and fix

Mismatch, rounding, label, or unit; owner to fix.

#### Step 5: Sign off

Reviewer initials and date; freeze version.

### Structured Output Template

# Tie-Out Log: [Deck]

**Deck version:** [ ]  |  **Model version:** [ ]  |  **Date:** [ ]

| Slide | Number | Unit | Source (file / tab / cell) | Source value | Match? | Issue | Owner | Fixed |
|---|---|---|---|---|---|---|---|---|

## Summary
Numbers checked: [ ]  |  Mismatches: [ ]  |  Fixed: [ ]

## Sign-off
[Name, date]

### Output Integration

#### Cross-Skill Integration

Feeds into: - the deck-qc playbook - Clean numbers - the final-readout playbook - Signed log

Pulls from: - the model-build playbook - Outputs - the fact-base playbook - Baselines

When this output goes to a teammate or reviewer, attach a handoff cover note: Brief, Backup, So-what, Ask. Never send a page without all four.

### Output Quality Self-Check

Before delivering, verify:

- ☐ Every number is traced

- ☐ Units and periods match

- ☐ Rounding rule is consistent

- ☐ Sign-off recorded

- ☐ Answer first: the so-what leads, the detail follows

- ☐ Sourced: every number and claim has a source or is marked as an assumption

- ☐ Voice: no em dashes; none of delve, leverage, utilize, unlock, harness, streamline, robust, cutting-edge

### Related Skills

- deck-qc - Production QC

- model-audit - Audit the model

- final-readout - Prepare the readout

## Playbook: Options Evaluation (name: options-evaluation)

### Quick Start

Say: Run the options-evaluation playbook Then provide: 1. The decision and the options considered 2. Criteria the client cares about (or I propose) 3. Evidence per option

I will structure options in the same format, weight and score against criteria with evidence, and show the sensitivity of the ranking to the weights.

Output: Delivered in chat. Export to Google Docs or Sheets and file in the client Outputs folder. Time: ~30 min

When to use: Develop phase when more than one path could answer the question

Phase: Develop

### Step 1: Diagnostic Questions

Instead of a generic intake, I ask only what the files cannot answer:

#### Question 1: The Criteria

"If you could pick three criteria, which would they be?"

Agree criteria before scoring to avoid reverse-engineering.

#### Question 2: The Do-Nothing

"What happens if we do nothing?"

Always score the base case.

### The Process

#### Step 1: List options

Include do-nothing; same format for each.

#### Step 2: Agree criteria and weights

With the sponsor before scoring.

#### Step 3: Score with evidence

1 to 5 with a one-line reason per score.

#### Step 4: Test weights

Does the winner change under reasonable weights?

#### Step 5: State the trade-offs

What you give up by choosing the winner.

### Structured Output Template

# Options Evaluation: [Decision]

## So-What
[Option B wins on X, trade-off Y]

## Options
| Option | Description | Value | Cost | Time | Risk |
|---|---|---|---|---|---|

## Scoring
| Criterion | Weight | Option A | Option B | Option C | Evidence |
|---|---|---|---|---|---|

## Weight Sensitivity
[ ]

## Trade-offs
[ ]

### Output Integration

#### Cross-Skill Integration

Feeds into: - the recommendation playbook - Chosen option - the slide-draft playbook - Options page - the risk-register playbook - Option risks

Pulls from: - the initiative-sizing playbook - Value - the root-cause-analysis playbook - Causes

When this output goes to a teammate or reviewer, attach a handoff cover note: Brief, Backup, So-what, Ask. Never send a page without all four.

### Output Quality Self-Check

Before delivering, verify:

- ☐ Do-nothing is included

- ☐ Criteria agreed before scoring

- ☐ Scores have reasons

- ☐ Weight sensitivity shown

- ☐ Trade-offs stated

- ☐ Answer first: the so-what leads, the detail follows

- ☐ Sourced: every number and claim has a source or is marked as an assumption

- ☐ Voice: no em dashes; none of delve, leverage, utilize, unlock, harness, streamline, robust, cutting-edge

### Related Skills

- recommendation - Write the recommendation

- scenario-sensitivity - Stress it

- decision-doc - Log the choice

## Playbook: Recommendation (name: recommendation)

### Quick Start

Say: Run the recommendation playbook Then provide: 1. Findings and chosen option 2. Financial case outputs 3. Decision requested

I will write the recommendation in answer-first form with the supporting argument, the conditions that must hold, and the explicit ask.

Output: Delivered in chat. Export to Google Docs or Sheets and file in the client Outputs folder. Time: ~30 min

When to use: Before the final SteerCo and when the storyline is converging

Phase: Recommend

### Step 1: Diagnostic Questions

Instead of a generic intake, I ask only what the files cannot answer:

#### Question 1: The Ask

"What exactly do you want the SteerCo to decide?"

The recommendation must end in a decision.

### The Process

#### Step 1: State the recommendation

One sentence with size of prize and timeframe.

#### Step 2: Give three reasons

Each backed by a finding and a number.

#### Step 3: Show the financial case

Run-rate, one-time cost, payback, range.

#### Step 4: State conditions and risks

What must be true and how it is mitigated.

#### Step 5: Make the ask

Decisions, owners, dates.

### Structured Output Template

# Recommendation: [Engagement]

## We recommend
[One sentence]

## Why
1. [Reason + proof number]
2.
3.

## Financial Case
| Metric | Low | Base | High |
|---|---|---|---|

## Conditions
[ ]

## Risks and Mitigation
[ ]

## The Ask
| Decision | Owner | By when |
|---|---|---|

### Output Integration

#### Cross-Skill Integration

Feeds into: - the storyline playbook - Governing thought - the final-readout playbook - Core content - the roadmap-build playbook - Plan to deliver

Pulls from: - the options-evaluation playbook - Choice - the scenario-sensitivity playbook - Case

When this output goes to a teammate or reviewer, attach a handoff cover note: Brief, Backup, So-what, Ask. Never send a page without all four.

### Output Quality Self-Check

Before delivering, verify:

- ☐ Answer first

- ☐ Three reasons, each with a number

- ☐ Conditions stated

- ☐ Ask is explicit

- ☐ Numbers tie to the model

- ☐ Answer first: the so-what leads, the detail follows

- ☐ Sourced: every number and claim has a source or is marked as an assumption

- ☐ Voice: no em dashes; none of delve, leverage, utilize, unlock, harness, streamline, robust, cutting-edge

### Related Skills

- storyline - Build the story

- final-readout - Build the readout

- roadmap-build - Build the roadmap

## Playbook: Roadmap Build (name: roadmap-build)

### Quick Start

Say: Run the roadmap-build playbook Then provide: 1. The recommendation and initiatives 2. Dependencies and constraints 3. Client owners

I will produce a sequenced 12-to-36-month roadmap with named client owners, KPIs, quick wins, and PMO governance.

Output: Delivered in chat. Export to Google Docs or Sheets and file in the client Outputs folder. Time: ~35 min

When to use: Recommend and Transition phases

Phase: Recommend and Transition

### Step 1: Diagnostic Questions

Instead of a generic intake, I ask only what the files cannot answer:

#### Question 1: The Owner

"Which named client leader owns each initiative?"

Without an owner, it is a wish.

### The Process

#### Step 1: List initiatives and milestones

#### Step 2: Sequence by dependency and value

Quick wins first.

#### Step 3: Assign client owners and KPIs

#### Step 4: Reality check capacity

With the implementation reviewer.

#### Step 5: Set governance

PMO, cadence, escalation.

### Structured Output Template

# Roadmap: [Engagement]

| Initiative | Owner | Q1 | Q2 | Q3 | Q4 | KPI | Run-rate value | Dependencies |
|---|---|---|---|---|---|---|---|---|

## Quick Wins (first 90 days)
[ ]

## Governance
[PMO, cadence, escalation]

### Output Integration

#### Cross-Skill Integration

Feeds into: - the final-readout playbook - Roadmap pages - the handover-pack playbook - Plan to hand over

Pulls from: - the recommendation playbook - Initiatives - the initiative-sizing playbook - Value

When this output goes to a teammate or reviewer, attach a handoff cover note: Brief, Backup, So-what, Ask. Never send a page without all four.

### Output Quality Self-Check

Before delivering, verify:

- ☐ Client owner per initiative

- ☐ KPIs defined

- ☐ Quick wins in 90 days

- ☐ Capacity checked

- ☐ Answer first: the so-what leads, the detail follows

- ☐ Sourced: every number and claim has a source or is marked as an assumption

- ☐ Voice: no em dashes; none of delve, leverage, utilize, unlock, harness, streamline, robust, cutting-edge

### Related Skills

- change-plan - Adoption

- handover-pack - Handover

- risk-register - Risks

## Playbook: Change Plan (name: change-plan)

### Quick Start

Say: Run the change-plan playbook Then provide: 1. The change and who is affected 2. Stakeholder map 3. Timeline

I will assess change readiness by group, craft the message and messenger for each, and set the first ask and a feedback loop.

Output: Delivered in chat. Export to Google Docs or Sheets and file in the client Outputs folder. Time: ~30 min

When to use: Develop and Recommend phases

Phase: Develop through Transition

### Step 1: Diagnostic Questions

Instead of a generic intake, I ask only what the files cannot answer:

#### Question 1: The Loss

"What do affected people lose, and what do they gain?"

Address the loss directly.

### The Process

#### Step 1: Segment groups

Size, what changes, what they lose and gain.

#### Step 2: Rate readiness

1 to 5 with evidence.

#### Step 3: Write messages and pick messengers

#### Step 4: Plan the first ask and the feedback loop

#### Step 5: Add to the risk register

Resistance risks.

### Structured Output Template

# Change Plan: [Engagement]

| Group | Size | What changes | Lose | Gain | Stance | Readiness | Message | Messenger | First ask |
|---|---|---|---|---|---|---|---|---|---|

## Communication Calendar
[ ]

## Feedback Loop
[ ]

### Output Integration

#### Cross-Skill Integration

Feeds into: - the roadmap-build playbook - Adoption steps - the risk-register playbook - Resistance risks

Pulls from: - the stakeholder-map playbook - Groups - the interview-synthesis playbook - Voice

When this output goes to a teammate or reviewer, attach a handoff cover note: Brief, Backup, So-what, Ask. Never send a page without all four.

### Output Quality Self-Check

Before delivering, verify:

- ☐ Each group has a message and messenger

- ☐ Readiness rated with evidence

- ☐ Feedback loop defined

- ☐ Answer first: the so-what leads, the detail follows

- ☐ Sourced: every number and claim has a source or is marked as an assumption

- ☐ Voice: no em dashes; none of delve, leverage, utilize, unlock, harness, streamline, robust, cutting-edge

### Related Skills

- roadmap-build - Roadmap

- stakeholder-map - Stakeholders

- risk-register - Risks

## Playbook: Storyline (name: storyline)

### Quick Start

Say: Run the storyline playbook Then provide: 1. The answer or current best answer 2. Audience and decision 3. Evidence so far

I will write the story as titles only (dot-dash), test that the titles read as a coherent argument, and map each page to the analysis behind it.

Output: Delivered in chat. Export to Google Docs or Sheets and file in the client Outputs folder. Time: ~30 min

When to use: Before building any deck; refresh at each gate

Phase: Develop and Recommend

### Step 1: Diagnostic Questions

Instead of a generic intake, I ask only what the files cannot answer:

#### Question 1: The Audience

"What does the SteerCo believe today, and what must they believe after?"

The storyline moves belief from A to B.

#### Question 2: The Order

"Does this argument go from answer to support, or from situation to answer?"

Exec audiences get answer first.

### The Process

#### Step 1: Write the governing thought

One sentence; the answer.

#### Step 2: Write SCQA

Situation, complication, question, answer.

#### Step 3: Write the key lines

Three to five supports; each a full sentence.

#### Step 4: Write dot-dash

One action title per page under each key line.

#### Step 5: Read the titles aloud

They must tell the whole story without the pages; fix gaps and repeats.

### Structured Output Template

# Storyline: [Engagement]

**Audience:** [ ]  |  **Decision:** [ ]  |  **Version:** [ ]

## Governing Thought
[ ]

## SCQA
S: [ ]  C: [ ]  Q: [ ]  A: [ ]

## Dot-Dash
**Key line 1:** [ ]
- Page: [Action title] | Evidence: [analysis] | Status: [Ghost / Draft / Tied]
- Page:

**Key line 2:** [ ]
- Page:

## Reading Test
[Notes on gaps or repeats]

### Output Integration

#### Cross-Skill Integration

Feeds into: - the ghost-deck playbook - Page list - the exec-summary playbook - Summary - the final-readout playbook - Outline

Pulls from: - the recommendation playbook - Answer - the hypothesis-draft playbook - Evidence

When this output goes to a teammate or reviewer, attach a handoff cover note: Brief, Backup, So-what, Ask. Never send a page without all four.

### Output Quality Self-Check

Before delivering, verify:

- ☐ Titles alone tell the story

- ☐ One message per page

- ☐ Each key line is a sentence

- ☐ Evidence is assigned to each page

- ☐ Decision is explicit at the end

- ☐ Answer first: the so-what leads, the detail follows

- ☐ Sourced: every number and claim has a source or is marked as an assumption

- ☐ Voice: no em dashes; none of delve, leverage, utilize, unlock, harness, streamline, robust, cutting-edge

### Related Skills

- ghost-deck - Sketch the pages

- exec-summary - Write the summary

- review-panel - Review the story

## Playbook: Ghost Deck (name: ghost-deck)

### Quick Start

Say: Run the ghost-deck playbook Then provide: 1. The storyline 2. Template and page budget 3. Data status

I will produce a page-by-page ghost deck with an action title, chart type, axes, expected so-what, data source, and status tag per page.

Output: Delivered in chat. Export to Google Docs or Sheets and file in the client Outputs folder. Time: ~35 min

When to use: As soon as the storyline exists; before analyses are final

Phase: Develop and Recommend

### Step 1: Diagnostic Questions

Instead of a generic intake, I ask only what the files cannot answer:

#### Question 1: The Page Budget

"How many main pages and how many appendix pages?"

Page limits force priorities.

### The Process

#### Step 1: List the pages

From dot-dash, in order.

#### Step 2: Write the action title

A full sentence with the so-what and a number if known.

#### Step 3: Choose the chart

Type, axes, units, highlight; see chart choices in the production guide.

#### Step 4: List data and owner

Model tab or source and who delivers it.

#### Step 5: Tag status

Ghost, Draft, Tied, Final.

### Structured Output Template

# Ghost Deck: [Engagement]

| # | Section | Action title | Chart / visual | Axes and units | Source (model tab / file) | Owner | Status | Due |
|---|---|---|---|---|---|---|---|---|

## Data Needs
[ ]

## Production Notes
[Template, fonts, think-cell, page limit]

### Output Integration

#### Cross-Skill Integration

Feeds into: - the slide-draft playbook - Pages to build - the number-tie-out playbook - Numbers to tie - the workplan-build playbook - Production tasks

Pulls from: - the storyline playbook - Pages - the model-build playbook - Data

When this output goes to a teammate or reviewer, attach a handoff cover note: Brief, Backup, So-what, Ask. Never send a page without all four.

### Output Quality Self-Check

Before delivering, verify:

- ☐ Every page has an action title

- ☐ Chart type is chosen and justified

- ☐ Source per page

- ☐ Status tag per page

- ☐ Page count within budget

- ☐ Answer first: the so-what leads, the detail follows

- ☐ Sourced: every number and claim has a source or is marked as an assumption

- ☐ Voice: no em dashes; none of delve, leverage, utilize, unlock, harness, streamline, robust, cutting-edge

### Related Skills

- slide-draft - Build pages

- deck-qc - QC the deck

- number-tie-out - Tie numbers

## Playbook: Slide Draft (name: slide-draft)

### Quick Start

Say: Run the slide-draft playbook Then provide: 1. The message of the slide 2. The data or analysis behind it 3. Audience

I will draft the slide spec (and a pptx page when asked) with the title, chart, annotations, takeaway box, and source line, following one-message-per-slide.

Output: Delivered in chat. Export to Google Docs or Sheets and file in the client Outputs folder. Time: ~10 min per slide

When to use: Turning an analysis into a page

Phase: Develop and Recommend

### Step 1: Diagnostic Questions

Instead of a generic intake, I ask only what the files cannot answer:

#### Question 1: The So-What

"What do you want the reader to conclude in 5 seconds?"

That sentence is the title.

### The Process

#### Step 1: Write the action title

Full sentence; verb; so-what; number.

#### Step 2: Pick the chart

Comparison: bar; trend: line; composition: stacked or waterfall; relationship: scatter; process: flow.

#### Step 3: Design the layout

Chart left, takeaway right; or chart full width with callouts.

#### Step 4: Annotate

Highlight the one bar or point that proves the title; remove the rest of the noise.

#### Step 5: Add source, units, and notes

Source line, units, date; speaker notes if presented.

### Structured Output Template

# Slide: [Title]

**Action title:** [ ]
**Chart:** [Type, axes, units, highlights]
**Layout:** [ ]
**Callouts:** [ ]
**Takeaway box:** [ ]
**Source:** [ ]
**Speaker notes:** [ ]
**Data location:** [model tab / cell]

### Output Integration

#### Cross-Skill Integration

Feeds into: - the deck-qc playbook - Slide for QC - the number-tie-out playbook - Numbers to tie

Pulls from: - the ghost-deck playbook - Plan - the scenario-sensitivity playbook - Charts

When this output goes to a teammate or reviewer, attach a handoff cover note: Brief, Backup, So-what, Ask. Never send a page without all four.

### Output Quality Self-Check

Before delivering, verify:

- ☐ Title is a full sentence

- ☐ One message only

- ☐ Chart supports the title

- ☐ Source and units present

- ☐ Passes the horizontal read test

- ☐ Answer first: the so-what leads, the detail follows

- ☐ Sourced: every number and claim has a source or is marked as an assumption

- ☐ Voice: no em dashes; none of delve, leverage, utilize, unlock, harness, streamline, robust, cutting-edge

### Related Skills

- ghost-deck - See the whole deck

- deck-qc - QC

- number-tie-out - Tie numbers

## Playbook: Executive Summary (name: exec-summary)

### Quick Start

Say: Run the exec-summary playbook Then provide: 1. The recommendation 2. Key numbers 3. Decision requested

I will write a one-page executive summary that a busy sponsor can read in two minutes and act on.

Output: Delivered in chat. Export to Google Docs or Sheets and file in the client Outputs folder. Time: ~20 min

When to use: Each SteerCo pre-read and the final readout

Phase: Recommend

### Step 1: Diagnostic Questions

Instead of a generic intake, I ask only what the files cannot answer:

#### Question 1: The Reader

"Will the reader see only this page?"

If yes, it must carry the whole case.

### The Process

#### Step 1: Lead with the answer

Recommendation and size of prize.

#### Step 2: Give three reasons

One sentence each with a number.

#### Step 3: State cost, timing, risks

Concise.

#### Step 4: End with the ask

Decision, owner, date.

#### Step 5: Cut 20%

Then check it still stands alone.

### Structured Output Template

# Executive Summary

**Recommendation:** [ ]

**Why:**
1. [ ]
2. [ ]
3. [ ]

**Investment and timing:** [ ]
**Key risks and mitigations:** [ ]
**Decisions requested:** [ ]

### Output Integration

#### Cross-Skill Integration

Feeds into: - the final-readout playbook - Opening page - the steerco-prep playbook - Pre-read

Pulls from: - the recommendation playbook - Answer - the storyline playbook - Key lines

When this output goes to a teammate or reviewer, attach a handoff cover note: Brief, Backup, So-what, Ask. Never send a page without all four.

### Output Quality Self-Check

Before delivering, verify:

- ☐ Stands alone

- ☐ Numbers tie

- ☐ Ask is explicit

- ☐ Under one page

- ☐ Answer first: the so-what leads, the detail follows

- ☐ Sourced: every number and claim has a source or is marked as an assumption

- ☐ Voice: no em dashes; none of delve, leverage, utilize, unlock, harness, streamline, robust, cutting-edge

### Related Skills

- storyline - Align to story

- final-readout - Use in readout

- number-tie-out - Tie numbers

## Playbook: Deck QC (name: deck-qc)

### Quick Start

Say: Run the deck-qc playbook Then provide: 1. The deck 2. Template rules 3. Version and audience

I will check a deck for story flow, title quality, number tie, formatting consistency, language, sources, and file hygiene, and return a fix list.

Output: Delivered in chat. Export to Google Docs or Sheets and file in the client Outputs folder. Time: ~30 min

When to use: Before any deck leaves the team

Phase: All

### Step 1: Diagnostic Questions

Instead of a generic intake, I ask only what the files cannot answer:

#### Question 1: The Version

"Which version is final, and who freezes it?"

Version control is part of QC.

### The Process

#### Step 1: Horizontal test

Read only the titles; story must hold.

#### Step 2: Slide by slide

One message; chart matches title; units; source.

#### Step 3: Format

Fonts, sizes, colors, alignment, spacing, page numbers, footers.

#### Step 4: Language

Spelling, tense, numbers format, abbreviations defined, no banned phrases.

#### Step 5: File hygiene

Remove comments, hidden slides, metadata, internal notes; save PDF and editable.

### Structured Output Template

# Deck QC: [Deck]

**Version:** [ ]  |  **Reviewer:** [ ]  |  **Date:** [ ]

## Verdict
[Ready / Fix then ready / Not ready]

## Findings
| # | Slide | Category | Issue | Fix | Owner | Done |
|---|---|---|---|---|---|---|

## Checks
- [ ] Horizontal flow
- [ ] Titles
- [ ] Numbers tie
- [ ] Formatting
- [ ] Language
- [ ] File hygiene

### Output Integration

#### Cross-Skill Integration

Feeds into: - the review-panel playbook - Clean deck - the final-readout playbook - Frozen version

Pulls from: - the number-tie-out playbook - Tie status - the slide-draft playbook - Slides

When this output goes to a teammate or reviewer, attach a handoff cover note: Brief, Backup, So-what, Ask. Never send a page without all four.

### Output Quality Self-Check

Before delivering, verify:

- ☐ Horizontal test run

- ☐ Every slide checked

- ☐ Comments and hidden slides removed

- ☐ PDF and editable saved

- ☐ Answer first: the so-what leads, the detail follows

- ☐ Sourced: every number and claim has a source or is marked as an assumption

- ☐ Voice: no em dashes; none of delve, leverage, utilize, unlock, harness, streamline, robust, cutting-edge

### Related Skills

- number-tie-out - Tie numbers

- review-panel - Panel review

- final-readout - Final readout

## Playbook: Final Readout (name: final-readout)

### Quick Start

Say: Run the final-readout playbook Then provide: 1. Recommendation and storyline 2. Audience and date 3. Decks and models status

I will build the readout outline, the page-by-page checklist, the red-team Q&A, and the pre-readout readiness list.

Output: Delivered in chat. Export to Google Docs or Sheets and file in the client Outputs folder. Time: ~40 min

When to use: Two weeks before the final SteerCo

Phase: Recommend

### Step 1: Diagnostic Questions

Instead of a generic intake, I ask only what the files cannot answer:

#### Question 1: The Decision

"What decision do we want at the end of the meeting?"

The ask drives the structure.

### The Process

#### Step 1: Build the outline

Nine sections per the template.

#### Step 2: Assign pages and owners

#### Step 3: Run reviews

Partner, QC, tie-out, model audit.

#### Step 4: Rehearse Q&A

Top ten questions.

#### Step 5: Freeze and stage

PDF and editable master; handover pack.

### Structured Output Template

# Final Readout: [Engagement]

## Outline
| Section | Pages | Content | Owner | Status |
|---|---|---|---|---|

## Q&A (Top 10)
| Question | Answer | Who |
|---|---|---|

## Readiness Checklist
- [ ] Sponsor pre-wired
- [ ] Pre-read sent
- [ ] Numbers tied
- [ ] Model audited
- [ ] Partner and QC review
- [ ] Version frozen

### Output Integration

#### Cross-Skill Integration

Feeds into: - the handover-pack playbook - Final materials - the retrospective playbook - Outcome

Pulls from: - the exec-summary playbook - Summary - the roadmap-build playbook - Roadmap

When this output goes to a teammate or reviewer, attach a handoff cover note: Brief, Backup, So-what, Ask. Never send a page without all four.

### Output Quality Self-Check

Before delivering, verify:

- ☐ Decision is explicit

- ☐ Numbers tied

- ☐ Model audited

- ☐ Q&A rehearsed

- ☐ Answer first: the so-what leads, the detail follows

- ☐ Sourced: every number and claim has a source or is marked as an assumption

- ☐ Voice: no em dashes; none of delve, leverage, utilize, unlock, harness, streamline, robust, cutting-edge

### Related Skills

- handover-pack - Hand over

- deck-qc - QC

- steerco-prep - SteerCo

## Playbook: Google Workspace Output (name: google-workspace-output)

### Quick Start

Say: Run the google-workspace-output playbook Then provide: 1. What to deliver (model, tracker, ghost deck, deck, or a conversion of an existing xlsx or pptx) 2. Where it should live (shared drive or folder) 3. Who needs access (team only, or a client counterpart)

I will check which Google connectors are available, choose the easiest route (CSV upload, copy of the Google starter, or in-place build), build it, verify the result, and set sharing the safe way.

Output: Delivered in chat. Export to Google Docs or Sheets and file in the client Outputs folder. Time: ~10 min for a tracker; ~30 to 60 min for a model or deck

When to use: The engagement uses Google Workspace, or a Google file is easier than building xlsx or pptx with Python

Phase: All

### Step 1: Diagnostic Questions

Instead of a generic intake, I ask only what the files cannot answer:

#### Question 1: The Approval

"Has the client approved Google Workspace for their data, in writing?"

If not, stop. Use the Office path locally and ask the EM.

#### Question 2: The Tier

"Which Google connectors are enabled here?"

Drive only means create and convert. Sheets and Slides editors mean in-place builds. If an editor is missing and the file already exists, I ask you to enable it instead of making a copy.

#### Question 3: The Audience

"Who opens the file, and do they need Excel or PowerPoint copies?"

Decides whether to export .xlsx, .pptx, or PDF at the end.

### The Process

#### Step 1: Check the format rule

Read Preferred output formats in engagement info. If blank, ask once and record the answer.

#### Step 2: Check approval and tools

Confirm client approval for Google. List the connectors available. Pick Tier 1, 2, or 3.

#### Step 3: Pick the route

Tracker or log: build a CSV and upload it to create a Google Sheet (Tier 1). Model: copy the Google starter, or create a blank Sheet and write inputs, formulas, and formats with the Sheets editor (Tier 2). Deck: copy the Slides starter and build pages with the Slides editor (Tier 3); charts are built on the Sheet Outputs tab and embedded as linked charts. Without the editor, deliver the spec and ask you to enable the connector.

#### Step 4: Build in one pass per step

One write for the data and formulas, one batch for formatting and tabs, one for slides. Parsing follows the Sheets UI: numbers as numbers, years and IDs with a leading apostrophe.

#### Step 5: Verify

Read values back. For models: no error values, Checks master flag is 0, Base outputs match the starter. For decks: read text, export a PDF where possible, check overflow, fonts, charts. If layout could not be checked visually, say so.

#### Step 6: Share and log

Share with named people only; reader or commenter for the client; never anyone-with-link. Record file name, link, owner, version, access, and approval in Client folder 01_Outputs/mcp-integration-logs/.

### Common Mistakes

- Making a second copy to avoid an edit: Edits go into the same file. Ask to enable the editor connector instead.

- Typed results: Every derived number is a formula, not a pasted result.

- Skipping the visual check: Converted decks can change fonts and spacing. Check every page.

### Structured Output Template

# Google Output Log: [Item]

**Date:** [ ]  |  **Owner:** [ ]  |  **Tier:** [1 / 2 / 3]  |  **Approval for client data:** [Y/N, where recorded]

| File | Type | Link | Route | Version | Shared with | Role |
|---|---|---|---|---|---|---|

## Verification
| Check | Result |
|---|---|
| Error values | |
| Master check | |
| Fonts and layout | |
| Charts linked | |

## Limits Noted
[ ]

### Output Integration

#### Cross-Skill Integration

Feeds into: - the number-tie-out playbook - Linked Outputs tab and charts - the deck-qc playbook - Deck to check - the handover-pack playbook - Files to hand over

Pulls from: - the model-spec playbook - What to build - the ghost-deck playbook - Pages to build - the connect-mcps playbook - Connectors

When this output goes to a teammate or reviewer, attach a handoff cover note: Brief, Backup, So-what, Ask. Never send a page without all four.

### Output Quality Self-Check

Before delivering, verify:

- ☐ Client approval for Google confirmed and recorded

- ☐ Edits went into the existing file, not a copy

- ☐ Every derived number is a formula

- ☐ Values read back with no error cells

- ☐ Sharing is to named people only

- ☐ Log saved

- ☐ Answer first: the so-what leads, the detail follows

- ☐ Sourced: every number and claim has a source or is marked as an assumption

- ☐ Voice: no em dashes; none of delve, leverage, utilize, unlock, harness, streamline, robust, cutting-edge

### Related Skills

- model-build - Excel route

- ghost-deck - Deck spec

- connect-mcps - Enable connectors

# Section B: Rhythm, governance and close

## Playbook: Daily Plan (name: daily-plan)

### Quick Start

Say: Run the daily-plan playbook Then provide: 1. Your role and today's calendar 2. Open assignments 3. Reviews due

I will produce a daily plan with a top three, review windows, handoff asks, and a check-out note.

Output: Delivered in chat. Export to Google Docs or Sheets and file in the client Outputs folder. Time: ~5 min

When to use: Start of every day, and end of day for the check-out

Phase: All

### Step 1: Diagnostic Questions

Instead of a generic intake, I ask only what the files cannot answer:

#### Question 1: The Top Three

"What three outputs make today a success?"

Anything else is a bonus.

### The Process

#### Step 1: Top three

With the deliverable and time block.

#### Step 2: Reviews and handoffs

Who needs what from you and by when.

#### Step 3: Check-in note

Priorities and risks for the team check-in.

#### Step 4: Check-out

What was done, what slipped, what is needed tomorrow.

### Structured Output Template

# Daily Plan: [Date]

## Top Three
1. [Output] - [time block]

## Reviews and Handoffs
| With | What | By |
|---|---|---|

## Check-in Note
[ ]

## Check-out
Done: [ ]  Slipped: [ ]  Need: [ ]

### Output Integration

#### Cross-Skill Integration

Feeds into: - the weekly-review playbook - Daily log

Pulls from: - the workplan-build playbook - Tasks - the handoff-brief playbook - Handoffs

When this output goes to a teammate or reviewer, attach a handoff cover note: Brief, Backup, So-what, Ask. Never send a page without all four.

### Output Quality Self-Check

Before delivering, verify:

- ☐ Three outputs, not tasks

- ☐ Review slots protected

- ☐ Check-out written

- ☐ Answer first: the so-what leads, the detail follows

- ☐ Sourced: every number and claim has a source or is marked as an assumption

- ☐ Voice: no em dashes; none of delve, leverage, utilize, unlock, harness, streamline, robust, cutting-edge

### Related Skills

- weekly-plan - Plan the week

- handoff-brief - Write handoffs

- status-update - Weekly status

## Playbook: Weekly Plan (name: weekly-plan)

### Quick Start

Say: Run the weekly-plan playbook Then provide: 1. Gate dates and SteerCo 2. Workplan 3. Team capacity

I will produce a weekly plan with deliverables by day, review windows, and a partner session agenda.

Output: Delivered in chat. Export to Google Docs or Sheets and file in the client Outputs folder. Time: ~10 min

When to use: Monday morning or Friday afternoon

Phase: All

### Step 1: Diagnostic Questions

Instead of a generic intake, I ask only what the files cannot answer:

#### Question 1: The Week's Outcome

"What must be true by Friday?"

Defines the weekly goal.

### The Process

#### Step 1: Set goals

Three outcomes tied to the next gate.

#### Step 2: Place deliverables by day

With review windows.

#### Step 3: Protect the review ladder

Draft to EM, then partner, with SLAs.

#### Step 4: Plan the partner session

Agenda and pre-read.

#### Step 5: Flag risks

Capacity, data, client.

### Structured Output Template

# Weekly Plan: [Week of]

## Goals
1. [ ]

## By Day
| Day | Deliverable | Owner | Review | Client touchpoint |
|---|---|---|---|---|

## Partner Session
[Agenda]

## Risks
[ ]

### Output Integration

#### Cross-Skill Integration

Feeds into: - the daily-plan playbook - Daily detail - the status-update playbook - Plan vs actual

Pulls from: - the workplan-build playbook - Tasks

When this output goes to a teammate or reviewer, attach a handoff cover note: Brief, Backup, So-what, Ask. Never send a page without all four.

### Output Quality Self-Check

Before delivering, verify:

- ☐ Goals link to a gate

- ☐ Review windows exist

- ☐ Capacity is realistic

- ☐ Answer first: the so-what leads, the detail follows

- ☐ Sourced: every number and claim has a source or is marked as an assumption

- ☐ Voice: no em dashes; none of delve, leverage, utilize, unlock, harness, streamline, robust, cutting-edge

### Related Skills

- daily-plan - Daily

- partner-session-prep - Partner session

- weekly-review - Review the week

## Playbook: Weekly Review (name: weekly-review)

### Quick Start

Say: Run the weekly-review playbook Then provide: 1. This week's outputs 2. Feedback received 3. Next week's gate

I will review the week against plan, update the learning log, and propose improvements to skills and templates.

Output: Delivered in chat. Export to Google Docs or Sheets and file in the client Outputs folder. Time: ~15 min

When to use: Friday afternoon

Phase: All

### Step 1: Diagnostic Questions

Instead of a generic intake, I ask only what the files cannot answer:

#### Question 1: The Lesson

"What is the one thing to change next week?"

Keep it to one.

### The Process

#### Step 1: Compare plan to actual

#### Step 2: Collect feedback

#### Step 3: Update the learning log

#### Step 4: Propose skill or template fixes

#### Step 5: Set next week's goals

### Structured Output Template

# Weekly Review: [Week]

## Plan vs Actual
[ ]
## Feedback
[ ]
## Learning Log
- [ ]
## Skill and Template Fixes
[ ]
## Next Week
[ ]

### Output Integration

#### Cross-Skill Integration

Feeds into: - the weekly-plan playbook - Goals

Pulls from: - the daily-plan playbook - Log - the status-update playbook - Status

When this output goes to a teammate or reviewer, attach a handoff cover note: Brief, Backup, So-what, Ask. Never send a page without all four.

### Output Quality Self-Check

Before delivering, verify:

- ☐ One lesson captured

- ☐ Fixes proposed

- ☐ Next week goals set

- ☐ Answer first: the so-what leads, the detail follows

- ☐ Sourced: every number and claim has a source or is marked as an assumption

- ☐ Voice: no em dashes; none of delve, leverage, utilize, unlock, harness, streamline, robust, cutting-edge

### Related Skills

- weekly-plan - Plan next week

- retrospective - Retro

## Playbook: Status Update (name: status-update)

### Quick Start

Say: Run the status-update playbook Then provide: 1. This week's progress 2. Risks and blockers 3. Decisions needed

I will write a one-page weekly status in answer-first form that a sponsor can read in 90 seconds.

Output: Delivered in chat. Export to Google Docs or Sheets and file in the client Outputs folder. Time: ~15 min

When to use: Weekly, before the sponsor touchpoint

Phase: All

### Step 1: Diagnostic Questions

Instead of a generic intake, I ask only what the files cannot answer:

#### Question 1: The Headline

"If the sponsor read one line, what should it say?"

Lead with it.

### The Process

#### Step 1: Headline

One line: on track, at risk, or off track and why.

#### Step 2: Findings

Three bullets with numbers.

#### Step 3: Progress vs plan

Done, in progress, slipped.

#### Step 4: Risks and blockers

With owner and ask.

#### Step 5: Decisions and next week

Who, what, by when.

### Structured Output Template

# Weekly Status: [Engagement] - [Date]

**Headline:** [ ]  |  **RAG:** [G/A/R]

## Findings
- [ ]

## Progress vs Plan
| Item | Status | Note |
|---|---|---|

## Risks and Blockers
| Item | Owner | Ask |
|---|---|---|

## Decisions Needed
| Decision | By whom | By when |
|---|---|---|

## Next Week
- [ ]

### Output Integration

#### Cross-Skill Integration

Feeds into: - the steerco-prep playbook - Progress - the weekly-review playbook - Input

Pulls from: - the workplan-build playbook - Progress - the risk-register playbook - Risks

When this output goes to a teammate or reviewer, attach a handoff cover note: Brief, Backup, So-what, Ask. Never send a page without all four.

### Output Quality Self-Check

Before delivering, verify:

- ☐ Headline states RAG and why

- ☐ Findings have numbers

- ☐ Asks have owners and dates

- ☐ Under one page

- ☐ Answer first: the so-what leads, the detail follows

- ☐ Sourced: every number and claim has a source or is marked as an assumption

- ☐ Voice: no em dashes; none of delve, leverage, utilize, unlock, harness, streamline, robust, cutting-edge

### Related Skills

- risk-register - Update risks

- decision-doc - Log decisions

- steerco-prep - Prep SteerCo

## Playbook: SteerCo Prep (name: steerco-prep)

### Quick Start

Say: Run the steerco-prep playbook Then provide: 1. SteerCo date and attendees 2. Decisions to be made 3. Content ready (decks, models)

I will produce the SteerCo agenda, pre-wire plan, pre-read checklist, expected objections with answers, and a decision log update.

Output: Delivered in chat. Export to Google Docs or Sheets and file in the client Outputs folder. Time: ~30 min

When to use: One week before each SteerCo and again 3 days before

Phase: All gates

### Step 1: Diagnostic Questions

Instead of a generic intake, I ask only what the files cannot answer:

#### Question 1: The Decision

"What must the SteerCo decide, and what is the fallback if they do not?"

A SteerCo without a decision is a status meeting.

### The Process

#### Step 1: Define decisions and outcomes

Per agenda item.

#### Step 2: Plan pre-wires

Sponsor first, then members; 2 to 3 days ahead.

#### Step 3: Send the pre-read

With a one-page summary.

#### Step 4: Rehearse objections

Top ten questions with answers; assign who answers.

#### Step 5: Capture outcomes

Decisions, actions, owners in the log within 24 hours.

### Structured Output Template

# SteerCo Prep: [Date]

## Agenda
| Time | Item | Lead | Decision / output |
|---|---|---|---|

## Pre-wire Plan
| Person | What to align on | By | Who |
|---|---|---|---|

## Pre-read Checklist
- [ ] Sent [date]
- [ ] Executive summary
- [ ] Decisions listed

## Likely Objections
| Question | Answer | Who answers |
|---|---|---|

## After the Meeting
[Decisions, actions, owners]

### Output Integration

#### Cross-Skill Integration

Feeds into: - the decision-doc playbook - Decisions - the status-update playbook - Next steps

Pulls from: - the stakeholder-map playbook - Pre-wires - the exec-summary playbook - Pre-read

When this output goes to a teammate or reviewer, attach a handoff cover note: Brief, Backup, So-what, Ask. Never send a page without all four.

### Output Quality Self-Check

Before delivering, verify:

- ☐ Decisions explicit per item

- ☐ Pre-wires done for each member

- ☐ Pre-read sent 2 to 3 days ahead

- ☐ Objection list rehearsed

- ☐ Outcomes logged

- ☐ Answer first: the so-what leads, the detail follows

- ☐ Sourced: every number and claim has a source or is marked as an assumption

- ☐ Voice: no em dashes; none of delve, leverage, utilize, unlock, harness, streamline, robust, cutting-edge

### Related Skills

- stakeholder-map - Plan pre-wires

- exec-summary - Write pre-read

- decision-doc - Log decisions

## Playbook: Partner Session Prep (name: partner-session-prep)

### Quick Start

Say: Run the partner-session-prep playbook Then provide: 1. The issue you need the partner's help with 2. Evidence so far 3. Time available

I will produce a one-page prep with the answer first, the evidence, the options you see, and the specific decision or steer you need.

Output: Delivered in chat. Export to Google Docs or Sheets and file in the client Outputs folder. Time: ~15 min

When to use: Before each of the two or more weekly partner sessions

Phase: All

### Step 1: Diagnostic Questions

Instead of a generic intake, I ask only what the files cannot answer:

#### Question 1: The Ask

"What exactly do you want from the partner: a decision, a steer, or an introduction?"

Partners have 30 minutes.

### The Process

#### Step 1: Lead with the answer

Current best view.

#### Step 2: Show the evidence

Three pages at most.

#### Step 3: State options

Each with a trade-off and your recommendation.

#### Step 4: State the ask

Decision or steer needed.

#### Step 5: Anticipate challenges

Top three questions.

### Structured Output Template

# Partner Session Prep: [Date]

**Answer so far:** [ ]
**Evidence:** [3 bullets]
**Options:** [A / B and recommendation]
**The ask:** [ ]
**Likely challenges:** [ ]
**Time:** [ ]

### Output Integration

#### Cross-Skill Integration

Feeds into: - the decision-doc playbook - Decisions

Pulls from: - the hypothesis-draft playbook - Answer status

When this output goes to a teammate or reviewer, attach a handoff cover note: Brief, Backup, So-what, Ask. Never send a page without all four.

### Output Quality Self-Check

Before delivering, verify:

- ☐ Answer first

- ☐ Ask is specific

- ☐ Evidence is three pages or fewer

- ☐ Answer first: the so-what leads, the detail follows

- ☐ Sourced: every number and claim has a source or is marked as an assumption

- ☐ Voice: no em dashes; none of delve, leverage, utilize, unlock, harness, streamline, robust, cutting-edge

### Related Skills

- steerco-prep - SteerCo

- decision-doc - Log decisions

- storyline - Story

## Playbook: Handoff Brief (name: handoff-brief)

### Quick Start

Say: Run the handoff-brief playbook Then provide: 1. The assignment or submission 2. To whom 3. By when

I will write a four-part handoff that lets the recipient start immediately and lets the reviewer check the work fast.

Output: Delivered in chat. Export to Google Docs or Sheets and file in the client Outputs folder. Time: ~5 min

When to use: Every time work changes hands

Phase: All

### Step 1: Diagnostic Questions

Instead of a generic intake, I ask only what the files cannot answer:

#### Question 1: The Output

"What exact output do you want back?"

Format and level of polish.

### The Process

#### Step 1: Brief

Question, hypothesis, format, data, constraints.

#### Step 2: Backup

Where the work and sources are.

#### Step 3: So-what

Expected or current finding and why it matters.

#### Step 4: Ask

What you need and by when; flag early if.

### Structured Output Template

# Handoff: [Topic]

**From / To / Needed by:** [ ]

## Brief
[ ]
## Backup
[ ]
## So-What
[ ]
## Ask
[ ]

### Output Integration

#### Cross-Skill Integration

Feeds into: - the daily-plan playbook - Asks

Pulls from: - the workplan-build playbook - Tasks

When this output goes to a teammate or reviewer, attach a handoff cover note: Brief, Backup, So-what, Ask. Never send a page without all four.

### Output Quality Self-Check

Before delivering, verify:

- ☐ All four parts present

- ☐ Needed-by time stated

- ☐ Backup link works

- ☐ Answer first: the so-what leads, the detail follows

- ☐ Sourced: every number and claim has a source or is marked as an assumption

- ☐ Voice: no em dashes; none of delve, leverage, utilize, unlock, harness, streamline, robust, cutting-edge

### Related Skills

- review-panel - Request review

- daily-plan - Plan the day

## Playbook: Meeting Agenda (name: meeting-agenda)

### Quick Start

Say: Run the meeting-agenda playbook Then provide: 1. Purpose and attendees 2. Length 3. Decisions needed

I will write a timed agenda with an owner and an output per item.

Output: Delivered in chat. Export to Google Docs or Sheets and file in the client Outputs folder. Time: ~5 min

When to use: Before any meeting with the client or partner

Phase: All

### Step 1: Diagnostic Questions

Instead of a generic intake, I ask only what the files cannot answer:

#### Question 1: The Outcome

"What is different after the meeting?"

Defines the agenda.

### The Process

#### Step 1: State purpose and outcome

#### Step 2: List items with owner and output

#### Step 3: Time-box

#### Step 4: Attach pre-read

### Structured Output Template

# Agenda: [Topic]

**Purpose / outcome:** [ ]

| Time | Item | Owner | Output |
|---|---|---|---|

**Pre-read:** [ ]

### Output Integration

#### Cross-Skill Integration

Feeds into: - the meeting-notes playbook - Notes

Pulls from: - the decision-doc playbook - Pending decisions

When this output goes to a teammate or reviewer, attach a handoff cover note: Brief, Backup, So-what, Ask. Never send a page without all four.

### Output Quality Self-Check

Before delivering, verify:

- ☐ Outcome is stated

- ☐ Timing adds up

- ☐ Pre-read attached

- ☐ Answer first: the so-what leads, the detail follows

- ☐ Sourced: every number and claim has a source or is marked as an assumption

- ☐ Voice: no em dashes; none of delve, leverage, utilize, unlock, harness, streamline, robust, cutting-edge

### Related Skills

- meeting-notes - Notes

- steerco-prep - SteerCo

## Playbook: Meeting Notes (name: meeting-notes)

### Quick Start

Say: Run the meeting-notes playbook Then provide: 1. Transcript or notes 2. Meeting type (client, SteerCo, team, partner) 3. Attendees

I will return decisions, actions with owners and dates, open questions, and signals about stakeholder stance within an hour of the meeting.

Output: Delivered in chat. Export to Google Docs or Sheets and file in the client Outputs folder. Time: ~10 min

When to use: After every client or partner meeting

Phase: All

### Step 1: Diagnostic Questions

Instead of a generic intake, I ask only what the files cannot answer:

#### Question 1: The Distribution

"Who gets the notes and when?"

Notes help only if they arrive fast.

### The Process

#### Step 1: Summarize in three lines

#### Step 2: List decisions

#### Step 3: List actions

Owner and date.

#### Step 4: Extract signals

Stance and hypothesis evidence.

#### Step 5: Send

Same day.

### Structured Output Template

# Meeting Notes: [Topic] - [Date]

**Attendees:** [ ]

## Summary
[3 lines]

## Decisions
- [ ]

## Actions
| Action | Owner | Due |
|---|---|---|

## Signals
[Stance, evidence]

### Output Integration

#### Cross-Skill Integration

Feeds into: - the decision-doc playbook - Decisions - the stakeholder-map playbook - Stance - the hypothesis-draft playbook - Evidence

Pulls from: - the steerco-prep playbook - Agenda

When this output goes to a teammate or reviewer, attach a handoff cover note: Brief, Backup, So-what, Ask. Never send a page without all four.

### Output Quality Self-Check

Before delivering, verify:

- ☐ Actions have owners and dates

- ☐ Decisions are unambiguous

- ☐ Sent same day

- ☐ Answer first: the so-what leads, the detail follows

- ☐ Sourced: every number and claim has a source or is marked as an assumption

- ☐ Voice: no em dashes; none of delve, leverage, utilize, unlock, harness, streamline, robust, cutting-edge

### Related Skills

- decision-doc - Log decisions

- stakeholder-map - Update map

- status-update - Status

## Playbook: Decision Doc (name: decision-doc)

### Quick Start

Say: Run the decision-doc playbook Then provide: 1. The decision taken or needed 2. Options and who decided 3. Date and forum

I will write a one-page decision record and update the decision log so scope, definitions, and approvals have a paper trail.

Output: Delivered in chat. Export to Google Docs or Sheets and file in the client Outputs folder. Time: ~10 min

When to use: After any SteerCo, scope change, definition agreement, or model assumption sign-off

Phase: All

### Step 1: Diagnostic Questions

Instead of a generic intake, I ask only what the files cannot answer:

#### Question 1: The Owner

"Who has the authority to make this decision?"

A decision by the wrong person will be reopened.

### The Process

#### Step 1: State the decision

One sentence.

#### Step 2: List options considered

Why rejected.

#### Step 3: Record owner, date, forum

#### Step 4: Record the reversal trigger

What would reopen it.

#### Step 5: Update the log and notify

Send to affected people.

### Structured Output Template

# Decision: [Topic]

**ID:** [D#]  |  **Date:** [ ]  |  **Forum:** [ ]  |  **Owner:** [ ]

## Decision
[ ]

## Context
[ ]

## Options Considered
| Option | Why not chosen |
|---|---|

## Impact
[Scope, timeline, model, deck]

## Reversal Trigger
[ ]

### Output Integration

#### Cross-Skill Integration

Feeds into: - the workplan-build playbook - Scope changes - the fact-base playbook - Definitions

Pulls from: - the steerco-prep playbook - Outcomes - the meeting-notes playbook - Context

When this output goes to a teammate or reviewer, attach a handoff cover note: Brief, Backup, So-what, Ask. Never send a page without all four.

### Output Quality Self-Check

Before delivering, verify:

- ☐ Owner has authority

- ☐ Reversal trigger stated

- ☐ Impact listed

- ☐ Log updated

- ☐ Answer first: the so-what leads, the detail follows

- ☐ Sourced: every number and claim has a source or is marked as an assumption

- ☐ Voice: no em dashes; none of delve, leverage, utilize, unlock, harness, streamline, robust, cutting-edge

### Related Skills

- steerco-prep - SteerCo outcomes

- workplan-build - Update plan

- fact-base - Update definitions

## Playbook: Risk Register (name: risk-register)

### Quick Start

Say: Run the risk-register playbook Then provide: 1. New risks or signals 2. Current register (if any) 3. Gate dates

I will update the register with likelihood, impact, early signals, mitigation, and owner, and recommend what to escalate.

Output: Delivered in chat. Export to Google Docs or Sheets and file in the client Outputs folder. Time: ~15 min

When to use: Weekly, and whenever a new risk appears

Phase: All

### Step 1: Diagnostic Questions

Instead of a generic intake, I ask only what the files cannot answer:

#### Question 1: The Signal

"What would we see first if this risk is materializing?"

Early signals make risks manageable.

### The Process

#### Step 1: Add or update risks

Category, description, likelihood, impact.

#### Step 2: Score

Likelihood x impact; escalate at 15 or more.

#### Step 3: Set mitigation and owner

#### Step 4: Update the heatmap

#### Step 5: Escalate

To EM or partner with a recommended action.

### Structured Output Template

# Risk Register: [Engagement] - [Date]

| ID | Risk | Category | L | I | Score | Early signal | Mitigation | Owner | Status |
|---|---|---|---|---|---|---|---|---|---|

## Escalate Now
[ ]

## Heatmap
[ ]

### Output Integration

#### Cross-Skill Integration

Feeds into: - the status-update playbook - Risks - the steerco-prep playbook - Escalations

Pulls from: - the status-update playbook - Signals

When this output goes to a teammate or reviewer, attach a handoff cover note: Brief, Backup, So-what, Ask. Never send a page without all four.

### Output Quality Self-Check

Before delivering, verify:

- ☐ Each risk has owner and mitigation

- ☐ Scores >= 15 escalated

- ☐ Early signals named

- ☐ Answer first: the so-what leads, the detail follows

- ☐ Sourced: every number and claim has a source or is marked as an assumption

- ☐ Voice: no em dashes; none of delve, leverage, utilize, unlock, harness, streamline, robust, cutting-edge

### Related Skills

- status-update - Report

- change-plan - Change risks

- recommendation - Delivery risks

## Playbook: Client Update Email (name: client-update-email)

### Quick Start

Say: Run the client-update-email playbook Then provide: 1. Purpose and recipient 2. Key message 3. Ask and date

I will draft a short, answer-first email in the client-exec voice with a clear ask.

Output: Delivered in chat. Export to Google Docs or Sheets and file in the client Outputs folder. Time: ~5 min

When to use: Whenever writing to the client

Phase: All

### Step 1: Diagnostic Questions

Instead of a generic intake, I ask only what the files cannot answer:

#### Question 1: The Ask

"What do you want the recipient to do, and by when?"

One ask per email.

### The Process

#### Step 1: Lead with the message

#### Step 2: State the ask and date

#### Step 3: Add only needed context

#### Step 4: Check tone

Match the recipient.

### Structured Output Template

Subject: [Message in one line]

[Recipient],

[Message in two sentences.]

[Ask and date.]

[Name]

### Output Integration

#### Cross-Skill Integration

Feeds into: - the status-update playbook - Updates

Pulls from: - the status-update playbook - Content

When this output goes to a teammate or reviewer, attach a handoff cover note: Brief, Backup, So-what, Ask. Never send a page without all four.

### Output Quality Self-Check

Before delivering, verify:

- ☐ One ask

- ☐ Under 150 words

- ☐ Tone fits

- ☐ Answer first: the so-what leads, the detail follows

- ☐ Sourced: every number and claim has a source or is marked as an assumption

- ☐ Voice: no em dashes; none of delve, leverage, utilize, unlock, harness, streamline, robust, cutting-edge

### Related Skills

- status-update - Status

- risk-register - Escalations

## Playbook: Engagement Health Check (name: engagement-health-check)

### Quick Start

Say: Run the engagement-health-check playbook Then provide: 1. Engagement and week 2. Any concerns 3. Who is asking (EM or partner)

I will score the engagement across eight dimensions with evidence, name the top two issues, and recommend actions.

Output: Delivered in chat. Export to Google Docs or Sheets and file in the client Outputs folder. Time: ~20 min

When to use: Every two weeks, and when something feels off

Phase: All

### Step 1: Diagnostic Questions

Instead of a generic intake, I ask only what the files cannot answer:

#### Question 1: The Pulse

"How does the sponsor feel about progress today?"

Relationship risk shows first in tone.

### The Process

#### Step 1: Score eight dimensions

Question, scope, answer, evidence, team, client, quality, financials.

#### Step 2: Cite evidence for each

#### Step 3: Name the top two issues

#### Step 4: Recommend actions

#### Step 5: Share with the EM

### Structured Output Template

# Health Check: [Engagement] - [Date]

| Dimension | RAG | Evidence | Action |
|---|---|---|---|
| Question and scope | | | |
| Answer and hypotheses | | | |
| Evidence and data | | | |
| Team load | | | |
| Client relationship | | | |
| Quality | | | |
| Financials | | | |
| Risks | | | |

## Top Two Issues
[ ]

### Output Integration

#### Cross-Skill Integration

Feeds into: - the status-update playbook - Issues

Pulls from: - the status-update playbook - Trend

When this output goes to a teammate or reviewer, attach a handoff cover note: Brief, Backup, So-what, Ask. Never send a page without all four.

### Output Quality Self-Check

Before delivering, verify:

- ☐ Evidence for each RAG

- ☐ Two issues named

- ☐ Actions proposed

- ☐ Answer first: the so-what leads, the detail follows

- ☐ Sourced: every number and claim has a source or is marked as an assumption

- ☐ Voice: no em dashes; none of delve, leverage, utilize, unlock, harness, streamline, robust, cutting-edge

### Related Skills

- risk-register - Risks

- decision-doc - Scope

## Playbook: Review Panel (name: review-panel)

### Quick Start

Say: Run the review-panel playbook Then provide: 1. The output to review (deck, model, memo) 2. Audience and stakes 3. Which reviewers (default: partner, EM, skeptic, client sponsor)

I will run each reviewer persona in turn, consolidate their feedback into one prioritized list, and flag contradictions between reviewers.

Output: Delivered in chat. Export to Google Docs or Sheets and file in the client Outputs folder. Time: ~20 min

When to use: Before an EM or partner review, and before any client-facing output

Phase: All

### Step 1: Diagnostic Questions

Instead of a generic intake, I ask only what the files cannot answer:

#### Question 1: The Stakes

"Is this going to a client or staying internal?"

Raises or lowers the bar and the number of reviewers.

### The Process

#### Step 1: Choose reviewers

Partner for story; EM for plan; skeptic for logic; sponsor and CFO for client view; QC for production.

#### Step 2: Run each persona

Each gives top three issues and one strength.

#### Step 3: Consolidate

Merge duplicates; rank by severity.

#### Step 4: Resolve conflicts

Where reviewers disagree, state the choice and why.

#### Step 5: Create the fix list

Owner and due date.

### Structured Output Template

# Review Panel: [Item]

## Verdict
[ ]

## Top Issues (ranked)
| # | Issue | Raised by | Severity | Fix | Owner |
|---|---|---|---|---|---|

## By Reviewer
**Partner:** [ ]
**EM:** [ ]
**Skeptic:** [ ]
**Client sponsor:** [ ]
**CFO:** [ ]
**QC:** [ ]

## Conflicts
[ ]

### Output Integration

#### Cross-Skill Integration

Feeds into: - the slide-draft playbook - Fixes - the model-build playbook - Fixes - the steerco-prep playbook - Readiness

Pulls from: - the deck-qc playbook - QC - the model-audit playbook - Audit

When this output goes to a teammate or reviewer, attach a handoff cover note: Brief, Backup, So-what, Ask. Never send a page without all four.

### Output Quality Self-Check

Before delivering, verify:

- ☐ Each persona gives specific, actionable feedback

- ☐ Conflicts are resolved

- ☐ Fix list has owners

- ☐ Answer first: the so-what leads, the detail follows

- ☐ Sourced: every number and claim has a source or is marked as an assumption

- ☐ Voice: no em dashes; none of delve, leverage, utilize, unlock, harness, streamline, robust, cutting-edge

### Related Skills

- deck-qc - QC the deck

- model-audit - Audit the model

- steerco-prep - Prepare the SteerCo

## Playbook: Handover Pack (name: handover-pack)

### Quick Start

Say: Run the handover-pack playbook Then provide: 1. The deliverables 2. Client owners 3. Handover date

I will compile an index, model user guide, assumptions list, open items, and a handover session agenda so the client can run the work without us.

Output: Delivered in chat. Export to Google Docs or Sheets and file in the client Outputs folder. Time: ~30 min

When to use: Transition phase

Phase: Transition

### Step 1: Diagnostic Questions

Instead of a generic intake, I ask only what the files cannot answer:

#### Question 1: The Owner

"Who owns the model after we leave?"

A model without an owner decays.

### The Process

#### Step 1: Index deliverables

#### Step 2: Write the model guide

Purpose, inputs, how to update, known limits.

#### Step 3: List open items and owners

#### Step 4: Plan the handover session

Walkthrough and Q&A.

#### Step 5: Return or delete data

Per agreement.

### Structured Output Template

# Handover Pack: [Engagement]

## Index
| Item | Location | Owner | Notes |
|---|---|---|---|

## Model Guide
[ ]

## Open Items
| Item | Owner | Date |
|---|---|---|

## Handover Session
[Agenda]

## Data Return and Deletion
[ ]

### Output Integration

#### Cross-Skill Integration

Feeds into: - the retrospective playbook - Closeout

Pulls from: - the final-readout playbook - Final materials - the roadmap-build playbook - Owners

When this output goes to a teammate or reviewer, attach a handoff cover note: Brief, Backup, So-what, Ask. Never send a page without all four.

### Output Quality Self-Check

Before delivering, verify:

- ☐ Client owner named for each item

- ☐ Model guide written

- ☐ Data return or deletion logged

- ☐ Answer first: the so-what leads, the detail follows

- ☐ Sourced: every number and claim has a source or is marked as an assumption

- ☐ Voice: no em dashes; none of delve, leverage, utilize, unlock, harness, streamline, robust, cutting-edge

### Related Skills

- retrospective - Retro

- knowledge-capture - Capture assets

- final-readout - Readout

## Playbook: Retrospective (name: retrospective)

### Quick Start

Say: Run the retrospective playbook Then provide: 1. Engagement outcome 2. Plan vs actuals 3. Team views

I will draft the retrospective with outcome snapshot, what worked, what to change, calibration table, and actions with owners.

Output: Delivered in chat. Export to Google Docs or Sheets and file in the client Outputs folder. Time: ~25 min

When to use: Within two weeks of the final SteerCo, and at a mid-engagement checkpoint on longer work

Phase: Close

### Step 1: Diagnostic Questions

Instead of a generic intake, I ask only what the files cannot answer:

#### Question 1: The Counterfactual

"If we ran this again, what is the first thing we would change?"

Surfaces the real lesson.

### The Process

#### Step 1: Snapshot outcome

#### Step 2: List what worked and why

#### Step 3: List what to change and root cause

#### Step 4: Fill calibration table

Plan vs actual.

#### Step 5: Agree actions

Owner, date.

### Structured Output Template

# Retrospective: [Engagement]

## Outcome
[ ]
## What Worked
[ ]
## What to Change
[ ]
## Calibration
| Item | Plan | Actual | Reason |
|---|---|---|---|
## Actions
| Action | Owner | Date |
|---|---|---|

### Output Integration

#### Cross-Skill Integration

Feeds into: - the knowledge-capture playbook - Assets - the proposal-draft playbook - Better estimates

Pulls from: - the handover-pack playbook - Closeout

When this output goes to a teammate or reviewer, attach a handoff cover note: Brief, Backup, So-what, Ask. Never send a page without all four.

### Output Quality Self-Check

Before delivering, verify:

- ☐ Root causes, not blame

- ☐ Calibration table filled

- ☐ Actions have owners

- ☐ Answer first: the so-what leads, the detail follows

- ☐ Sourced: every number and claim has a source or is marked as an assumption

- ☐ Voice: no em dashes; none of delve, leverage, utilize, unlock, harness, streamline, robust, cutting-edge

### Related Skills

- knowledge-capture - Capture assets

- weekly-review - Weekly review

## Playbook: Knowledge Capture (name: knowledge-capture)

### Quick Start

Say: Run the knowledge-capture playbook Then provide: 1. The engagement 2. Assets worth keeping 3. Confidentiality limits

I will classify what is reusable, strip confidential detail, and write a short case summary and an asset index.

Output: Delivered in chat. Export to Google Docs or Sheets and file in the client Outputs folder. Time: ~25 min

When to use: After the retro

Phase: Close

### Step 1: Diagnostic Questions

Instead of a generic intake, I ask only what the files cannot answer:

#### Question 1: The Limit

"What client information must never leave the engagement folder?"

Strip it first.

### The Process

#### Step 1: List assets

#### Step 2: Anonymize

#### Step 3: Write a short case

Situation, approach, result.

#### Step 4: Index with tags

#### Step 5: Store in the firm knowledge base

Via the user.

### Structured Output Template

# Knowledge Capture: [Engagement]

## Case Summary
[Situation / approach / result, anonymized]

## Asset Index
| Asset | Type | Location | Reusable? | Confidentiality | Owner |
|---|---|---|---|---|---|

### Output Integration

#### Cross-Skill Integration

Feeds into: - the proposal-draft playbook - Credentials

Pulls from: - the retrospective playbook - Learnings

When this output goes to a teammate or reviewer, attach a handoff cover note: Brief, Backup, So-what, Ask. Never send a page without all four.

### Output Quality Self-Check

Before delivering, verify:

- ☐ Client identifiers removed

- ☐ Assets tagged

- ☐ Owner named

- ☐ Answer first: the so-what leads, the detail follows

- ☐ Sourced: every number and claim has a source or is marked as an assumption

- ☐ Voice: no em dashes; none of delve, leverage, utilize, unlock, harness, streamline, robust, cutting-edge

### Related Skills

- retrospective - Retro

- proposal-draft - Reuse